## Cover Sheet
Programme | Professional Record Standards Body Transfers of Care | DOCUMENT RECORD ID KEY
Sub-Prog / Project | Hospital discharge, Mental health discharge, Emergency care discharge and generic outpatient letter projects
Clinical leads | John Williams, RCGP - hospital discharge James Read, RCPsych, mental health discharge Tom Hughes, RCEM, Emergency care discharge Jonathan Brown, RCP and BSG and Phil Koczan, RCGP - outpatient letters
Owner | Jan Hoogewerf | Version | 0.5
Author | Jan Hoogewerf, Darren Wooldridge, Annette Gilmore, Nicola Quinn
Version Date | 27.06.2017 | Status | Draft

## Document Control
| Programme | Professional Record Standards Body Transfer of Care Programme | DOCUMENT RECORD ID KEY
| Sub-Prog / Project | Hospital discharge, Mental health discharge, Emergency care discharge and generic outpatient letters projects
| Clinical leads | John Williams, RCGP - hospital discharge James Read, RCPsych, mental health discharge Tom Hughes, RCEM, Emergency care discharge Jonathan Brown, RCP and BSG and Phil Koczan, RCGP, outpatient letters
| Owner | Jan Hoogewerf | Version | 1
| Author | Jan Hoogewerf, Darren Wooldridge, Annette Gilmore,Nicola Quinn
| Version Date | 10.11.2017 | Status | Final
Amendment History:
Version | Date | Amended By | Amendment History
Separate clinical safety reports were produced for each of the transfer of care projects undertaken to date (hospital discharge, mental health and emergency care). These have been combined into a single report as similar hazards were identified across all three transfers. | Various. | Authors see above | Developed by authors and reviewed by clinical leads and clinical advisers on each project and subsequently by the project boards for each project.
0.1 | 11.01.17
0.2 | 13.01.17 | Jan Hoogewerf | Minor updates, typos etc.
0.3 | 26.06.17 | Jan Hoogewerf | Updated to include outpatients
0.4 | 27.06.17 | Jan Hoogewerf | Updated to include implementation risks
0.5 | 27.07.17 | Jan Hoogewerf | Version updated in response to feedback from NHS Digital Clinical Safety Officers
1 | 10.11.17 | Thomas Hobbs | Version updated with new branding for publication
Forecast Changes:
Anticipated Change | When
TBA | TBA
Reviewers:
This document must be reviewed by the following:
Name | Signature | Title / Responsibility | Date | Version
NHS Digital Clinical Safety Group |  |  |  | 0.5
Approvals:
This document must be approved by the following:
Name | Signature | Title / Responsibility | Date | Version
NHS Digital Clinical Safety Group |  | Clinical Safety Group
Distribution:
Name | Signature | Title / Responsibility | Date | Version

## Hazard log
Hazard Number | Hazard Name | Hazard Description | Hazard Causes | Patient Safety Impact Description | Initial Risk Ranking |  |  | Dependencies and Assumptions | Existing Controls / Mitigations | Additional Controls / Mitigations |  |  |  | Residual Hazard Risk Rating |  |  | Summary of Actions/Additional Comments | Additional Comments
| Hazard Name |  |  |  | Likelihood | Consequence | Risk Acceptability |  |  | Design | Technical Assurance | Training | Business Processes | Likelihood | Consequence | Risk Acceptability
Generic Hazards
1 | Critical data absent as not recorded | Critical data absent because it is not recorded. | Critical data not entered in the system, e.g. because clinician is not prompted for it or forgets to record it. | Incorrect treatment or advice may be given based on incomplete clinical information | High | Significant | 3 | Addressed by use of headings and information models. Also addressed by training in good recording practice and by adherence to Mandatory and Required fields as set out in implementation guidance. | Include headings and fields to capture critical data. Include coded text to indicate the absence of information eg allergies and adverse reactions, if none are recorded, clinician must record ‘no known allergies’ or ‘no information available’. Guidance to Implementers: This issue/risk might arise in use or misuse of our product. | Mitigated By Design |  | Training in good recording practice |  | Significant | Significant | 2 | 1. Headings added to reduce likelihood. 2. Guidance provided to Implementers. 3. Residual risk transferred (with guidance) to implementers.
2 | Coded data which is not human readable | If coded information is carried without associated text it may not be comprehensible. | Sending organisation using codes other than SNOMED CT or using SNOMED CT codes which are not in the set supported by recipient system. | Incorrect diagnosis or treatment. | High | Significant | 3 | Systems should display associated text with each coded item. Only SNOMED CT should be used. | Include associated text with any coded field. Only use SNOMED CT in discharge communications (eg not READ, OPCS etc,) Guidance to Implementers: This issue/risk might arise in use or misuse of our product. | Mitigated By Design |  |  |  | Significant | Significant | 2 | 1. Communications will only support SNOMED CT. 2. Guidance provided to Implementers. 3. Residual risk transferred (with guidance) to implementers.
3 | Inconsistent use of headings | Inconsistent use of headings. i.e. The names and definitions of headings need to match between primary/secondary care/social care etc. | Inconsistencies in data transfer between systems | Incorrect data transfer, so that the data is presented under an inappropriate heading, resulting in it being missed or misinterpreted by the care professional | High | Significant | 3 | Multi-professional consultation to address whether headings (and definitions) match those used by/needed by end users. | Include heading and data field definitions. Guidance to Implementers: Implementers have to ensure they have the most up to date version of the headings, and that the headings are correctly implemented in their system(s). | Mitigated By Design |  |  |  | Significant | Significant | 2 | 1. Headings to be clearly defined. 2. The people using these headings need to be trained to use them. 3. Guidance provided to Implementers. 4. Residual risk transferred (with guidance) to implementers.
4 | Too many headings | Too many headings will be time consuming and burdensome and may result in omission of key clinical information. | Headings design issue. | Critical clinical information may be omitted, having an adverse effect on patient safety. | High | Considerable | 3 |  | Although the requirement is for IT systems to support all the headings, not all headings will be mandatory for implementers. It is anticipated that local trading agreements will determine the optional headings to be used by a particular community, but that where they are used they must match those in the record standard. Also pre-population will be used wherever possible to reduce burden on user. | Logical grouping for the practice setting. The headings have gone through several levels of consultation to make sure there are not too many headings. | Prepopulation where appropriate. | Users trained to use headings appropriately. | Complete only fields relevant to individual patient/specialty | Significant | Considerable | 2
5 | System does not support headings | Clinicians unable to add information because the headings are not in the system. | System design issue. | Critical clinical information may be omitted having an adverse effect on patient safety. | High | Considerable | 3 | Inclusion of headings in electronic health records. | Include requirement for headings in system procurement and configuration. Test that the system can support the headings |  | Test that the system can support the headings |  |  | Significant | Considerable | 3
6 | Incompatible prescribing formats | Conversion from hospital (dose based prescribing) format to GP (product based prescribing) format may lead to errors, compounded by the tendency for one dose based prescription to map to more than one product based prescription. As a result the wrong product may be selected which may be hazardous or ineffective for the patient. | A dose based medication item from hospital may be converted to the wrong product based medication item in primary care either as a result of human transcription error or as a result of automated or semi-automated conversion | Patient given inappropriate medication. | Significant | Major | 3 | Hospital e-prescribing systems implement the structured/coded medications information model specified in the hospital discharge summary project. | Human readable rendition of original dose based prescription preserved and presented to Primary care prescriber to facilitate cross check. Primary care clinican review of the hospital prescription and decision made about future prescribing rather than dependency on fully automated conversion process | Medication information model for dsicharge summary. | Thorough clinical safety testing of any clinical software solution both around time of developing soiftware and around time of deployment |  |  | Not possible to assess at this stage - will depend on how interoperable dose syntax is implemented but in view of potentially serious consequences MUST be reduced to lower likelihood than for totally human conversion process | Major | 3
7 | Headings are not understandable to the patient | Patients/carers with access to their records are unhappy with the content as they cannot understand it. | Headings are not understandable to the patient or patients are not happy with the clinicians population of the headings. | Patient dissatisfaction, reducing engagement with their treatment. | High | Considerable | 3 | Headings are comprehensible to patients. | Patients have been involved with the design of the headings to ensure they are understandable and appropriate from a patient perspective. | Headings use terms that are comprehensible to patients. |  | Train clinicians to record information appropriately. |  | Significant | Considerable | 3
8 | Blank fields | Lack of clarity over what a blank field signifies (i.e. not recorded, not assessed, not present etc) | Due to the design | Recipients will have insufficient information to make appropriate clinical decisions. | High | Major | 4 |  | Implementation guidance states for optional fields that if a field is left blank the heading should not be communicated in the message. If a field is mandatory, the implementation guidance includes coded text for what should be recorded. |  | System design should reduce this. |  |  | Significant | Major | 3
9 | Lack of clarity about prescriber responsibility | Confusion about whether a new medication item in the discharge summary is to be continued and whether an item has been changed/discontinued. | Clinicians may be unsure of the status of the medication or be unaware that a change has happened to the medication status. | Patient receiving incorrect or no medication as clinician has insufficient information to make appropriate clinical decisions. | High | Considerable | 3 | Implementation of e-prescribing systeme in hospitals which support the medications information models in the discharge summary. | Discharge summary phase 2 medications information model. | Mitigated By Design | System design should reduce this. | Train clinicians to provide full medication records in discharge summary. |  | Significant | Considerable | 3
10 | Inappropriate auto population of information | Inappropriate auto population could lead to excessive, superfluous information creating difficulty for the recipient to focus on the pertinent information. | Inappropriate auto population of information | The recipient may miss important information and not provide appropriate treatment. | High | Considerable | 3 | Trading agreement between local organisations which agrees parameters for the data to be included in discharge summary, eg which optional headings to be included. | Headings specify "relevant" where there is danger of superfluous information e.g. "relevant past medical, surgical, mental health history". | Headings specify that only relevant information should be recorded. | System design should reduce this. | Clinicians encouraged to review autopopulated information to make sure it is relevant. |  | Significant | Considerable | 3
11 | Misidentification of patient | Correct patient may not be identifiable from the information provided. | Unique identifier unknown or entered incorrectly e.g. NHS number entered incorrectly | If patient is misidentified they may not receive appropriate treatment. | High | Major | 3 | Use of NHS number to identify the patient uniquely. | The NPSA recommends that the NHS number is used to correctly identify a patient. | System should be linked to the patient demographic service (PDS) to obtain NHS number |  | Clinicians encouraged to use the patient demographic service to identify the patient. |  | Significant | Major | 3
12 | Lack of alignment with other standards | The standards may not be consistent with the latest version of related standards e.g. dm+d, SNOMED CT subsets | As existing standards are updated they may be misaligned to the headings. | Lack of standardisation across health/care records used in different sites. | High | Major | 3 |  | Maintenance of the standards is the responsibility of the PRSB and changes must be possible for integration with relevant data standards as they change. |  |  |  |  | Significant | Major | 3
13 | Un-read discharge summaries | Recipients of the discharge summary do not read/act upon them. | Recipients may be unaware that the discharge summary has been automatically uploaded in their system. | Clinicians unaware of the patient’s attendance. | High | Major | 3 | Discharge summaries must not be automatically uploaded onto the GP system without review. | Implementation guidance states no automatic upload and audit trail to ensure individual review of discharge summary contents. | Migitated by system design. | Audit trail to identify reviewer of discharge summary. |  | Process within GP practice to handle shared inbox. | Significant | Considerable | 3
14 | Lack of clarity about required actions | Recipients of the discharge summary are unclear about what is expected of them for the ongoing care of the patient. | Clinicians completing the discharge summary do not clearly specify who is responsible for required actions. | Patient receiving incorrect or no treatment as clinician fails to act upon the required actions described in the discharge summary. | High | Major | 3 | Discharge summaries include plan and requested actions. | Use of headings and sub-headings to specify contents of plan section should include the action to be taken and who should be responsible (eg hospital or GP). | Migitated by system design. |  | Training in good recording practice |  | Significant | Considerable | 3
15 | Legal issues | Users may not be able to adequately complete the legal information headings. | Lack of understanding about medicolegal issues. | Medicolegal issues may arise if users are not aware of the legal implications of their actions. | High | Significant | 3 |  | The descriptions under the legal headings provide clarity about what is to be recorded. | Training on medicolegal issues. |  |  |  | Significant | Significant | 2
16 | Coded data which is not human readable | If coded information is carried without associated text it may not be comprehensible. | Sending organisation using codes other than SNOMED CT or using SNOMED CT codes which are not in the set supported by recipient system. | Incorrect diagnosis or treatment. | High | Significant | 3 | Systems should display associated text with each coded item. Only SNOMED CT should be used. | Include associated text with any coded field. Only use SNOMED CT in outpatient communications (eg not READ, OPCS etc,) Guidance to Implementers: This issue/risk might arise in use or misuse of our product. | Mitigated By Design |  |  |  | Significant | Significant | 2 | 1. Communications will only support SNOMED CT. 2. Guidance provided to Implementers. 3. Residual risk transferred (with guidance) to implementers.
Mental Health Specific Hazards
17 | Inaccurate or out of date information | Incorrect or out of date information. | Erroneous information may have been entered into the record or old and outdated information carried over from previous entries. | Incorrect information may be present in the record. Depending on what this is, this could lead to incorrect, delayed or no treatment. It could also lead to significant personal distress for the patient. | Significant | Considerable | 3 | For good information governance and an audit trail, system design should allow for the ability to differentiate between the person making the record entry and the person who authored the record entry. All entries should be dated and provenance recorded. | Mental health discharge summary information is contemporaneous. The person completing the record is included in the message and it is mandatory that their contact details are also included in the communication to ensure they can be contacted if clarification on the information communicated is required. The date the record was completed is included in the message. Implementation guidance provided. | System design should reduce this. |  | User training |  | Significant | Considerable | 3 | 1. Guidance provided to Implementers. 2. Residual risk transferred (with guidance) to implementers.
18 | Headings are not appropriate for patients with mental health care needs | Care professionals are unfamiliar with the language used in the headings and clinical descriptions | Headings and clinical descriptions are not those that are used in mental health care services. | Important information is missing or entered in the wrong place leading to inappropriate care. Inappropriate clinical language may cause distress to patient and relatives. | Significant | Significant | 2 | The headings have been developed from wide consultations with experts in mental health and with patients. | The language in the headings and descriptions and implementation guidance are appropriate for patient with mental health care needs and the service needs. Guidance for implementers. | Mitigated By Design |  |  |  | Moderate | Significant | 2 | 1. Headings and descriptions appropriate for use case. 2. Guidance provided to Implementers. 3. Residual risk transferred (with guidance) to implementers. 4. Risk also transferred to those responsible for training.
19 | Key information may be overlooked. | Certain information of particular importance may be overlooked (e.g. Mental Health Act status, key worker/ care coordinator contact details, safety alerts.) causing patient harm. | Headings are not prominent enough. | Clinicians may be unaware of this key clinical information and therefore do not take these into consideration when treating the patient. | Significant | Major | 3 |  | Mandation and 'required' for key headings. These items to have a prominent position on the system template. Guidance to implementers. | System design so reduce this. |  | Users trained to use headings appropriately. |  | Low | Major | 2 | Fields that are mandatory to complete must have ability to complete a null value e.g. 'no GP' . Fields that are 'required' should record the information if there is information available e.g. Key worker/ care coordinator contact details, care planning documentation.
20 | Grouping of headings not appropriate for practice setting | Grouping of headings is not appropriate for the practice setting resulting in inaccurate or missing information. | The headings are grouped in a way that doesn’t work for a speciality/service/clinician. | Information will either be missed or put into the incorrect heading which could be propagated through the patient journey. | Significant | Major | 3 |  | Multidisciplinary input from a wide range of specialities, included in consultation. Piloting of headings in different practice settings in live use may be required. | System design should reduce this. Template design groups headings in support of clinical practice. |  |  |  | Moderate | Considerable | 2 | 1. Guidance provided to implementers. 2. Residual risk transferred (with guidance) to implementers.
21 | High risk conditions | Failing to identify a critical clinical condition e.g paranoid schizophrenia, borderline personality disorder, suicide risk. | Lack of a place to clearly recognise the condition. | If the underlying conditions are not recognised and appropriate care given the patient may become a safety risk to self and/ or others. | Significant | Major | 3 |  | Clinical headings were developed from consultations with experts in mental health. They support the ability to record and communiate the pertinent information required to identify and evaluate criticality and high risk conditions e.g. diagnoses, clinical summary, safety alerts, actions and requested actions. Implementation guidance provided. | Existing methods for identification of high risk patients should continue to be used, eg patient held information, care plans. |  |  |  | Low | Major | 2
22 | Different statutory and legal requirements across the four UK countries | Certain headings will have different statutory and legal requirements and applications in the four UK countries e.g. Mental Health Act, Deprivation of Liberty Safeguards, Mental Capacity Assessments, Care planning arrangements etc. | Confusion by clinicians about which headings are relevant to the country in which they work. | Confusion for clinicians who are not aware of the correct requirements, which may result in the patient receiving inappropriate care. | Significant | Significant | 2 |  | The clinical descriptions under the legal and statutory requirement headings provide clarity about what is to be recorded. Implementation guidance refers to the relevant legislation and statutory requirements in each country. | System design should reduce this. |  | Clinicians know what is required in theri practice. Training on country specific issues. |  | Low | Significant | 1
Outpatient Specific Hazards
23 | Lack of clarity about required actions | Recipients of the outpatient letter are unclear about what is expected of them for the ongoing care of the patient. | Clinicians completing the outpatient letter do not clearly specify who is responsible for required actions. | Patient receiving incorrect or no treatment as clinician fails to act upon the required actions described in the outpatient letter. | High | Major | 3 | Outpatient letters include plan and requested actions for healthcare professionals. | Use of headings and sub-headings to specify contents of plan section should include the action to be taken and who should be responsible (eg outpatient clinic or GP). | Migitated by system design. |  | Training in good recording practice |  | Significant | Considerable | 3
Generic Implementation Hazards
24 | Unavailable information | Information missed out as system already implemented is too structured/ inflexible to include headings. | E.g. Already structured systems, which cannot be changed or only at high cost. | Incorrect treatment as a result of insufficient information. | High | Considerable | 3 | [10 empty] | System implementation / user interface design issue.
25 | Electronic system failure | If the headings are only designed for use in electronic systems, there is a risk that there is no fall back if the system is not available. | Critical problem of system. | Inability to record patient data. | High | Catastrophic | 5 | [10 empty] | This is a disaster recovery/business continuity matter - out of scope.
26 | Confidentiality issues | There may be some information (such as sexual health information) that patients do not want recorded on a shared record. | Autopopulation of sensitive information or failure of clinician to discuss what information was acceptable to be included. | Violations of privacy may cause great distress to the patient. | High | Significant | 2 | [10 empty] | This is an information governance matter.
27 | Cross boundary interpretation | Incorrect interpretation/ translation of clinical information. | Incorrect interpretation/ translation of clinical information . | Incorrect clinical information. | Medium | Considerable | 2 | [10 empty] | Cross boundary implementation matter
28 | Poor template design | Clinicians use the clinical template as a tick box exercise and do not put sufficient thought into process. | Clinicians use the template as a tick box exercise and do not put sufficient thought into the process. | Use of template leads to inaccurate/missing information. | High | Major | 3 |  | Clinicians involved in template design. |  |  | Training in use of templates | [5 empty] | System implementation/ user interface design issue.
29 | Actions taken by unqualified clinicians | Users undertaking actions for which they are unqualified | As the heading is in the record users may feel that are supposed to complete it. | Care professionals undertaking actions without appropriate qualifications will be likely to make clinical errors. | High | Major | 4 |  |  | This is an implementation issue which would be addressed by IT systems displaying different headings or list of assessment tools for different staff groups, depending on their qualifications. It could also be addressed by staff training. | Training issue for users to work within their competency.
30 | Refusal to adopt the standard | Services may refuse to use the record standard. | Lack of support for the standard. | If some services do not adopt the standard there will remain a lack of interoperability between services. | High | Major | 4 |  | Muti professional involvement in the development of the standard to ensure it is fit for purpose. | Communication and dissemination strategy to stress the benefits of using the standard. | PRSB, NHS Digital to take a leadership role in encouraging implementation.
31 | Inability to exchange information | Different coding systems used in different sites will limit exchange and re-use of data. | Different coding systems used in different sites. | Incorrect clinical information. | High | Major | 4 |  | Only SNOMED CT can be carried in the message in coded format. Textual representation of the code must be provided for every coded entry. A separate national initiative is underway to move GP practice systems to SNOMED CT by June 2017. | [8 empty] | Cross boundary implementation issue.
32 | Policy/statutory evolution | As policy/statutory requirements change the current headings will be obsolete. | Statutory requirements change all the time. | Use of obsolete headings mean required information may not be captured. | High | Major | 4 |  | Maintenance of the standards is the responsibility of the PRSB and changes must be possible for integration with relevant data standards as they change.
33 | Temporary GP registration | There may instances where a patient has a registered GP practice but is treated as a temporary registration (e.g. whilst on holiday) by another practice. There is a risk that the EC discharge summary will only be sent to the registered GP practice. | EC system functionality may only allow discharge summaries to be sent to the patient’s registered GP practice. | Temporary doctor, who has the most immediate need of the discharge summary, may not receive the discharge summary, impacting patient care. | High | Major | 4
Emergency Care Specific Implementation Hazards
34 | Use of diagnosis qualifiers | EC use diagnosis qualifiers to indicate certainty of diagnoses. If the qualifier indicating ‘working diagnosis’ is separated from the diagnosis code it may be taken to be ‘final diagnosis’. | Separation of diagnosis qualifier from diagnosis SNOMED CT code. | Inappropriate treatment as clinical decision support may indicate an inappropriate medication e.g. working diagnosis of ischemic heart disease (IHD) may trigger prescription of statins. | High | Major | 4
35 | Recording allergies as diagnoses | If allergic causative agents are recorded using SNOMED CT diagnosis codes, the GP system will not be able to use the code in prescribing decision support. | GP system prescribing decision support uses allergic agents rather than diagnosis codes, so they would not be picked up in prescribing contraindications. | Risk of allergic reaction as GPs are unaware of the allergic agent. | High | Catastrophic | 5

## Hazard Workshop Attendees (hidden)
1st Project Workshop

## Risk matrix
Risk matrix
Risk acceptability
Likelihood | Very High | 3 | 4 | 4 | 5 | 5
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4
| Low | 1 | 2 | 2 | 3 | 4
| Very low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic
Consequence
Likelihood | [6 empty] | Consequence
Category | Likelihood | [5 empty] | Category | Interpretation
Very High | Unacceptable level of risk. Mandatory elimination or control to reduce risk to an acceptable level. | [6 empty] | Consequence | Patients Affected
High | Unacceptable level of risk. Mandatory elimination or control to reduce risk to an acceptable level | [5 empty] | Catastrophic | Death | Multiple
Medium | Undesirable level of risk. Attempts should be made to eliminate or control to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical. | [6 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
Low | Tolerable where cost of further reduction outweighs benefits gained.
Very Low | Acceptable, no further action required | [5 empty] | Major | Death | Single
[8 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
[8 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
[8 empty] | Severe psychological trauma | Multiple
[7 empty] | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
[8 empty] | Severe psychological trauma | Single
[8 empty] | Minor injury or injuries from which recovery is not expected in the short term. | Multiple
[8 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
[8 empty] | Minor injury from which recovery is expected in the short term | Multiple
[8 empty] | Minor psychological upset; inconvenience | Multiple
[7 empty] | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single