## Cover Page
Clinical Safety Hazard Log - Ambulance Handover to ED Standard
Programme | PRSB Standards Development
Sub-Prog / Project
Prog. Director | Martin Orton | Status | Approved
Owner | Martin Orton | Version | 1
Author | Darren Wooldridge | Version Date | 21.02.2020
Clinical Safety Hazard Log - Ambulance Handover to ED Standard
Document Purpose
Copyright © 2017, Health and Social Care Information Centre. NHS Digital is the trading name of the Health and Social Care Information Centre.All Rights Reserved.
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please complete the fields as indicated in blue.

## Version History (hidden)
Amendment History
Version | Date | Amendment History
0.1 | 04.03.2008 | First draft Hazard Log
1 | 04.03.2008 | Approved document
2 | 14.04.2008 | Revised in line with product description, Hazard and Mitigation removed, Hazard Description and Mitigation added.
2.1 | 20.05.2010 | Revised in line with latest PSA guidance
2.2 | 30.05.2011 | Revised following comments from CSOs
3 | 16.08.2011 | Formal issue
3.1 | 01.04.2013 | Rebranded with HSCIC
3.2 | 16.09.2013 | Likelihood description table included in Risk Matrix tab
3.3 | 25.09.2013 | Change to programme name. Rotation of Likelihood and Consequence columns as per PSA guidelines.
3.4 | 07.11.2016 | Rebranded with NHS Digital
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
|  | NHS Digital Clinical Safety Team | 07.11.2016 | 3.4
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Stuart Harrison |  | Head of Safety Engineering | 07.11.2016 | 3.4
Dr Manpreet Pujara |  | Clinical Director for Patient Safety | 07.11.2016 | 3.4
Distribution
NHS Digital Clinical Safety Personnel
Document Status:
The controlled copy of this document is maintained in the NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## Version History
Amendment History
Version | Date | Amendment History
0.1 |  | 1st version
0.2 | 25.3.19 | Updated after review with project clinical safety officer
0.6 | 06.06.19 | Updated by the project clinical safety officer (Version number was jumped to match other documents)
0.7 | 16.08.19 | Updated the version history reviewers and approvers
0.8 | 08.11.19 | Updated in response to NHSD Clinical Safety Group comments
0.9 | 03.01.20 | Updated in response to NHSD Clinical Safety Group comments
1 | 21.02.20 | Updated to V1 with approval dates after NHSD Clinical Safety Group approval
Reviewers
This document must be reviewed by the following:
Name |  | Status | Date | Version
Tom Hughes |  | Reviewed | 03.01.20 | 0.9
David Davies |  | Reviewed | 29.08.19 | 0.6
PRSB Assurance Committee |  | Reviewed | 14.10.19 | 0.6
Project Board |  | Reviewed | 29.08.19 | 0.6
Approved
This document must be approved by the following:
Name |  | Status | Date | Version
Tom Hughes (Clinical Safety Officer) |  | Approved | 03.01.20 | 0.9
Project Board |  | Approved | 29.08.19 | 0.6
NHS Digital Clinical Safety Group |  | Approved | 19.02.20 | 0.9

## Hazards Log
Digital Interoperability Platform Hazard Log
Hazard |  |  |  | Cause |  | Unmodified Risk |  |  | Mitigation |  |  |  | Modified Risk |  |  | Admin
Hazard Number | Hazard Name | Hazard Description | Potential Clinical Impact | Possible Causes | Existing Controls | Consequence | Likelihood | Risk | Design | Test | Training | BPC | Consequence | Likelihood | Risk | Summary of Actions/Notes | Owner | Status
1 | Misidentification of the patient | The patient is wrongly identified by the clinicians providing care. | Healthcare provider delivers inappropriate health care based on inaccurate clinical information leading to patient harm | 1) Patients may have very similar/identical names 2) Patients may have very similar/identical birth dates 3) Patients may have very similar/identical NHS numbers 4) Passing on wrong identification of the patient from the ambulance crew/system | The ambulance dataset (ADS ISN) once fully defined and associated clinical safety case report / hazard log | Major | Low | 3 | 1) Requirement for access to the Spine 2) NHS number matching |  |  |  | Major | Very Low | 2 | Risk inherited in the ambulance handover to secondary care care project - however this risk is inherent in the ambulance dataset project and is thus passed onto this project for mitigation
2 | Inaccurate/missing data | Data is not populated accurately in ambulance record. | Healthcare provider delivers inappropriate health care based on missing/inaccurate clinical information leading to patient harm | 1) Clinician unaware of the requirement to record safety significant data 2) Clinician forgets to record safety significant data 3) User interface not easy for clinicians to navigate and to record data safely and accurately. 4) Autopopulated data is not updated and therefore becomes out of date. | As above | Considerable | Low | 2 |  |  | 1) Recommend training/training materials in good recording practise |  | Considerable | Very Low | 2 | Risk inherited in the ambulance handover to secondary care care project - however this risk is inherent in the ambulance dataset project and is thus passed onto this project for mitigation
3 | Suppliers presenting the information in a way which is inappropriate for end users | Potential for clinicians to be unable to use the system approriately. | Misinterpretation/misunderstanding of information. | Poor interface design |  | Considerable | High | 3 | 1) Implementation guidance has been provided to support suppliers with implementing the standards in their systems. 2) Users should be invoved in the system design | 1) Users should be invovled in the system testing |  | PRSB will write to the Ambulance Dataset (ADS) project to alert them to this risk and to request that a usability assessment e.g. compliance with ISO standard e.g. https://www.iso.org/standard/63500.html be incorporated into the ADS ISN | Considerable | Low | 2 | Recommend PRSB to develop example templates to demonstrate clinically appropriate presentation of data
4 | Complexity of the standard inhibits clinician recording of clinical safety significant data | Healthcare providers record clinical safety significant data in different formats e.g. using free text | Healthcare provider misinterprets clinical safety significant data and delivers inappropriate care leading to to patient(s) harm. | Tension between structured information and free text |  | Considerable | High | 3 | 1) System design should reduce burden on end users e.g. use of auto-population where appropriate. 2) End users have been involved in the design of the standards to ensure the content is appropriate. |  | 1) Provide training in use of the standard 2) Guidance has been provided on what should be recorded under each heading. | 1) The standards will be evaluated on an on-going basis by the PRSB. Consideration for free text has been incorporated into the design and provided not only at a question level but also at an overarching level for the care event. | Considerable | Low | 2 | Risk inherited in the ambulance handover to secondary care care project - however this risk is inherent in the ambulance dataset project and is thus passed onto this project for mitigation
5 | Failure to adopt record standard | Service providers may refuse to adopt and use the record standard | Failure to deliver optimum care based on inconsistent guidance leading to patient(s) harm/death | End-users choose not to apply standard |  | Considerable | Medium | 3 |  |  |  | 1) RCEM and CoP provided clinical leadership for the project 2) Consistent data structures defined in ADS and ECDS 3) Communication of the standards by NHS Digital, PRSB, College of Paremedics and Royal College of Emergency Medicine. 4) Championing by stakeholder organisations who have provided endorsement for the standards. | Considerable | Low | 2
6 | Burden on clinicians | Unrealistic data burden for clinician means critical safety items are not completed | Healthcare provider delivers inappropriate health care based on incomplete clinical information leading to patient harm | Cognitive overload / poor interface or system design / inadequate data checks/ validation |  | Considerable | Medium | 3 | 1) Include prompts reminding clinician to enter safety significant data 2) Clear use cases for data entry and proof of user-centred design of the user interface (e.g. measures of usability) 3) Inclusion of mandatory fields to prevent sending of messages without key information 4) Automation of as many fields as possible to avoid manual entry of information |  |  |  | Considerable | Low | 2 | Risk inherited in the ambulance handover to secondary care care project - however this risk is inherent in the ambulance dataset project and is thus passed onto this project for mitigation
7 | Unsafe transmission of CPR information | Transmission of data regarding CPR decisions without provenance of the data | Healthcare provider is unsure of the provenance of the CPR decision information and is thus unable to be sure of actions to take regarding CPR. | Provenance of the data is unavailable |  | Catastrophic | Very High | 5 | 1) System design must not allow any transmission of CPR decision information unless the provenance is provided. |  |  |  | Major | Low | 3 | The DNACPR element was not included in the standard to remove the risk of wrongly not performing CPR. This leaves the lesser risk of doing unwanted / inappropriate CPR.

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | No. of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term. | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
|  | Risk Acceptability | [5 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible severity | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required